## Agile Estimates
| Requirements | Value Points | User Story Points | Bang for the Buck | * Value Points (client; importance of the requirement) * Story Points (developer; effort of the development team in fulfilling the requirement)
Login/Logout | Admin should be able to login/logout. | 13 | 34 | 0.38235
Bike Map | Admin should be able to view the bike map. | 8 | 55 | 0.14545
Search | Admin should be able to search for a bike, user or issue. | 5 | 3 | 1.6667
Bike Records | Admin should be able to view bike records. | 13 | 1 | 13
| Admin should be able to add a bike record. | 13 | 8 | 1.625
| Admin should be able to delete a bike record. | 13 | 5 | 2.6
User Records | Admin should be able to view user records. | 5 | 2 | 2.5
| Admin should be able to change a user's eligibility | 3 | 13 | 0.23077
Issues | Admin should be able to view bike issues. | 2 | 2 | 1
| Admin should be able to change an issue's status. | 1 | 13 | 0.076923
Database | Server should be able to sync the database with the web and android apps. | 8 | 21 | 0.38095

## Sheet1 (hidden)
Requirements | Value Points | User Story Points | * Value Points (client; importance of the requirement) * Story Points (developer; effort of the development team in fulfilling the requirement)
Admin should be able to login/logout. |  | 34
Admin should be able to view the bike map. |  | 55 | 1, 1, 2, 3, 5, 8, 13, 21, 34, 55
Admin should be able to search for a bike, user or issue. |  | 3
Admin should be able to view bike records. |  | 1
Admin should be able to add a bike record. |  | 8
Admin should be able to delete a bike record. |  | 5
Admin should be able to view user records. |  | 2
Admin should be able to change a user's eligibility |  | 13
Admin should be able to view bike issues. |  | 2
Admin should be able to change an issue's status. |  | 13
Server should be able to sync the database with the web and android apps. |  | 21