CS 192 Software Engineering II
Implementation Plan

In this sheet, record planned activities for the sprint. This should be updated per sprint and submitted to the instructor.
Sprint No.	Date	Activity	Accountability / (Name of Person)	Output	Remarks
1	1/27/2016	Plan and prepare Sprint Review Checklist	Kirzten Marquez	Implementation Plan
	1/30/2016	Code login/logout functionality	Kirzten Marquez	Source Code
	2/5/2016	Code bike management	Carlos Penaflorida	Source Code
	2/5/2016	Test login/logout functionality	Carlos Penaflorida	Test Scorecard Result	Use Test Scorecard done in CS 191
	2/5/2016	Test bike management	Alezon Valerio	Test Scorecard Result	Use Test Scorecard done in CS 191
	2/5/2016	Code Review	Alezon Valerio	Code Review Result
	2/5/2016	Sprint Review	Kirzten Marquez	Sprint Review Document
	2/5/2016	Sprint Retrospect	Kirzten Marquez	Sprint Retrospect Document	Link to Sprint Release Codes in GitHub
2	2/10/2016	Plan and prepare Sprint Review Checklist	Kirzten Marquez	Implementation Plan
	2/17/2016	Code bike issue management	Carlos Penaflorida	Source Code
		Code issue status editing	Carlos Penaflorida	Source Code
	2/19/2016	Test bike issue management	Alezon Valerio	Test Scorecard Result	Use Test Scorecard done in CS 191
		Test issue status editing	Kirzten Marquez	Test Scorecard Result	Use Test Scorecard done in CS 191
	2/19/2016	Code Review	Alezon Valerio	Code Review Result
		Review with Client	Kirzten Marquez	Sprint Review Document (from client)
	2/19/2016	Sprint Review	Kirzten Marquez	Sprint Review Document
	2/19/2016	Sprint Retrospect	Kirzten Marquez	Sprint Retrospect Document	Link to Sprint Release Codes in GitHub
3	2/23/2016	Plan and prepare Sprint Review Checklist	Kirzten Marquez	Implementation Plan
		Code frontend for admin	Alezon Valerio	Source Code
		Code bike map	Kirzten Marquez	Source Code
		Change database framework	Carlos Penaflorida	Source Code/Schema
		Test bike map	Kirzten Marquez	Test Scorecard Result		Use Test Scorecard done in CS 191
		Code Review	Alezon Valerio	Code Review Result
		Review with Client	Kirzten Marquez	Sprint Review Document (from client)
		Sprint Review	Alezon Valerio	Sprint Review Document
		Sprint Retrospect	Carlos Penaflorida	Sprint Retrospect Document		Link to Sprint Release Codes in GitHub

4	3/9/2016	Plan and prepare Sprint Review Checklist	Kirzten Marquez	Implementation Plan
		Code responsive bike map	Alezon Valerio	Source Code
		Code issue sorting	Kirzten Marquez	Source Code
		Code analytics	Carlos Penaflorida	Source Code/Schema
		Test responsive bike map	Carlos Penaflorida	Test Scorecard Result	Use Test Scorecard done in CS 191
		Test issue sorting	Alezon Valerio	Test Scorecard Result	Use Test Scorecard done in CS 191
		Test analytics	Kirzten Marquez	Test Scorecard Result	Use Test Scorecard done in CS 191
		Code Review	Alezon Valerio	Code Review Result
		Review with Client	Kirzten Marquez	Sprint Review Document (from client)
		Sprint Review	Alezon Valerio	Sprint Review Document
		Sprint Retrospect	Carlos Penaflorida	Sprint Retrospect Document	Link to Sprint Release Codes in GitHub

5	4/5/2016	Plan and prepare Sprint Review Checklist	Kirzten Marquez	Implementation Plan
		Fix code for report categories / bike states	Kirzten Marquez	Source Code
		Code employee assignment	Alezon Valerio	Source Code
		Code analytics	Carlos Penaflorida	Source Code/Schema
		Test report categories / bike states	Alezon Valerio	Test Scorecard Result	Use Test Scorecard done in CS 191
		Test employee assignment	Carlos Penaflorida	Test Scorecard Result	Use Test Scorecard done in CS 191
		Test analytics	Kirzten Marquez	Test Scorecard Result	Use Test Scorecard done in CS 191
		Code Review	Alezon Valerio	Code Review Result
		Review with Client	Kirzten Marquez	Sprint Review Document (from client)
		Sprint Review	Alezon Valerio	Sprint Review Document
		Sprint Retrospect	Carlos Penaflorida	Sprint Retrospect Document	Link to Sprint Release Codes in GitHub